## Slide 1: LLIN distribution in Suriname
An effective strategy to control malaria
N. Cerson - van Eer and H. Cairo
Seminar on activities based on LLIN interventions; San Pedro, Belize 11 – 12 May 2011

## Slide 2: Background

## Slide 3: Country profile
The Republic of Suriname is located at the north-east coast of South-America
Between French Guiana in the east, Guyana in the west, Brazil in the south and the Atlantic Ocean in the North
Occupying an area of about 163,830 km2.
With slightly more than 500.000 inhabitants

## Slide 4: Population at risk
The population at risk ca. 77.000 comprises of two different groups:
  the stable village population and
  the mobile/unstable population.
The populated interior can be stratified in three main areas
  Amerindians villages
  Maroon villages
  Garimpos, gold mining areas

## Slide 6: Malaria control in Suriname

## Slide 7: National coordination structure
The Ministry of Health (MOH) in Surinam is responsible for all actions related to malaria.
A national malaria board function as the main technical advisory group for the policy making process.

## Slide 8: History of malaria control in Suriname
Beginning of the 20th century focus on case management and chemoprophylaxis for travelers
From 1949 to 1955: larval control and residual insecticide spraying as main strategies.
In 1958: MEP adopted.
Transformation of the Insect Control Program into the MEP accordingly.

## Slide 9: History continued
The MEP focused on the following strategies:
  Vector control:
  Active Case Detection:
  Case management:
The MEP resulted in the elimination of malaria from the coastal area in Suriname
The MEP did not succeed in eliminating malaria from the interior

## Slide 10: History continued
In 1984: the operational malaria control activities in the interior were transferred to Medical Mission Primary Health Care Suriname (MMPHS)
The Medical Mission PHCS has 56 health post in the interior staffed with 105 healthcare assistants and 23 microscopist
In 1997: the MM introduced ITN for all villages in the interior

## Slide 13
French Guyana
Brazil
Guyana
Suriname
region1
Region 1
Region 5
Region 3
Region 2
Region 4
Region 5

## Slide 14: Malaria burden
Malaria cases started to increase since the late 1980s
0
2000
4000
6000
8000
10000
12000
14000
65
67
69
71
73
75
77
79
81
83
85
87
89
91
93
95
97
99
2001
2003
2005

## Slide 15: Age groups affected by malaria

## Slide 16: The National Malaria Board
In 1995 the National Malaria Board was installed
The policy of malaria control and prevention in Suriname has been translated in four main strategies:
  Free Rapid diagnosis and prompt effective treatment.
  Free Distribution of LLINs to the population in areas of risk.
  Behavior Change Communication (BCC/IEC)
  Selective vector control (with emphasis on the use of LLINs).

## Slide 17: Preparations for LLINs Distribution

## Slide 18: Consent building and community support
Meetings were held with tribal leaders to gain consent and support
Consultations were held to re-design nets to meet the expectations of target populations

## Slide 22: KAP studies
A baseline MIS was conducted in 2006 in stable communities and in 2009 in the mobile communities
Key findings for stable communities were as follows:
  About 70% of both groups had ever used a net and most people knew where to obtain a net
  75% of the Amerindians were using a mosquito net to prevent malaria
  < 50% of the Maroons were using a mosquito net

## Slide 23: KAP studies continued
Key findings in the gold miner population:
59.2% knew that a bed net was to protect oneself against malaria
47.4% use a bed nets to protect themselves against mosquitoes
59.4 % of the respondents had slept with a bed net the previous night
The main reason mentioned to not use a bed net is not having one.

## Slide 24: Awareness campaign
A social scientist was contracted to design and execute a BCC/IEC campaign
  DVDs
  Poster
  Brochures
  Focus group discussions
Campaign launched prior to distribution and continued after the distribution

## Slide 26: Forecasting and Procurement
The MM registration database was used to forecast the number of nets needed
A census was done in gold mining areas
Procurement was done by the PEU for MM Malaria Program
Procurement was done by the procurement department of the MOH for the gold miners program

## Slide 27: Forecasting and Procurement cont.
Companies were selected after competitive international bidding
LLINs were stored centrally at the Bureau of Public Health

## Slide 28: Distribution of LLINs
Transportation to the interior by car, airplane and boat (ATV in gold mining areas)
The already existing logistics of the Medical Mission PHCS was used for the distribution
For gold mining areas sentinel sites were selected to function as intermediate storage
People had to identify themselves with the MM registration card
Gold miners did not have to identify themselves

## Slide 31: Coverage reached
The Medical Mission Malaria Program distributed about 55.998 from 2006 – 2008
Reaching over 90 % coverage of the target population
The MoH Malaria Program distributed 14.065 in 2010
Reaching 94% coverage of estimated gold miners population

## Slide 32: Monitoring & Evaluation

## Slide 33: M & E surveys
After 3 months of distribution M & E surveys were conducting
Very low percentage of usage revealed 12%
  Color of the nets
  Privacy issues
Led to locally designed combination bed net and replacement of previous LLINs
Surveys conducted in 2010 in stable communities revealed 60% - 91% use

## Slide 34: Entomological surveys
Entomological surveillance extended to cover gold mining areas
  Adult mosquito monitoring (population density and sp. determination)
  Larval studies (breeding sites and sp. Determination)
  Resistance and residual studies

## Slide 35: Lessons Learned
Understanding the customs of mosquito net use is essential in the successful implementation of LLIN as malaria control strategy

## Slide 36: Impact of different control strategies

## Slide 37: Impact of different control strategies
Malaria transmission in Suriname has decreased significantly over the past seven years, a period in which important and large-scale integrated control activities took place, including the mass-distribution of Lon Lasting Impregnated Nets (LLINs).
  a dramatic decline in the number of malaria cases
  a significant decrease in hospitalization
  a tremendous decrease in mortality
  a significant decrease in the An. darlingi population

## Slide 38
Deaths resulting from Malaria: from 2001 to 2009:
Year | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009
Mortality malaria | 24 | 23 | 16 | 18 | 7 | 2 | 0 | 0 | 0 | 1
Year | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009
Hospital admissions | 217 | 323 | 377 | 163 | 153 | 50 | 35 | 47 | 22
Hospital admissions: from 2001 to 2009:

## Slide 39
Chart: 
| 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009
POS | 11361 | 15937 | 12837 | 15006 | 9823 | 9131 | 3289 | 1732 | 1489 | 535
Quinine + Doxy or Clinda ACT ACT Plus
Flooding

## Slide 40
2001

## Slide 41
2002

## Slide 42
2003

## Slide 43
2004

## Slide 44
2005

## Slide 45
2006

## Slide 46
2007

## Slide 47
2008

## Slide 49: Thank you!