## Slide 1
Preparing for the Switch
Next steps for the
Polio Eradication and Endgame Strategic Plan 2013-2018 (PEESP)
in the Region of the Americas
Dr. Maria Cristina Pedreira
Dr. Gloria Rey
Ms. Elizabeth Thrush
Elluminate Session
9 April 2015

## Slide 2: Objectives of the Polio Eradication & Endgame Strategic Plan 2013-2018
1
Detect and interrupt all poliovirus transmission
2
Strengthen immunization systems, and withdraw oral polio vaccines (OPV)
3
Contain poliovirus and certify interruption of transmission
4
Plan polio’s legacy

## Slide 3
Timeline: Switch and containment activities
Chart: 
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Immediately
Form National Certification Committees
Confirm date of last WPV2
Assign National Polio Containment Coordinator
2015
2016
Adjust tOPV and bOPV orders
Switch monitors identified
IMPLEMENT
Train monitors
Train health staff
Distribute bOPV
SWITCH PERIOD
VALIDATE
tOPV disposal
Validation by switch monitors
Validation by NCC
tOPV and bOPV 2016
tOPV inventory
Draft Switch Plan
Inventory of Labs that store WPV, PV Sabin and potentially infectious materials
Destroy all WPV2 or contain in essential facilities
destroy or contain PV Sabin 2 in essential facilities
World Health Assembly
SAGE
Confirmation of switch dates
Prepare
Establish management structure

## Slide 4: National (or Sub-Regional) Certification Comittees
Members of the committee should be:
  independent leading experts in relevant disciplines
  (public health, epidemiology, virology, etc.)
  acting in personal capacity, without direct responsibility for polio eradication in their countries or sub-regions.
NCC will be responsible to:
Assess the achievement of the four main objectives of the Polio Eradication & Endgame .
Review reports and documentation on laboratory containment
Review report on validation of tOPV recall and destruction
Submit report to the Regional Certification Commission.

## Slide 5: National Certification Comittees
Send to PAHO by the end of April the names and specialties of each member as well as the contact details of the President of the National or Sub-Regional Certification Committee:
Name
Telephone
Address
Email
Information received from: HON, NIC

## Slide 6: Certification of the Eradication of WPV2
Every country should send a formal statement declaring when the last case of WPV2 was detected to the RCC through PAHO by mid-April.
  Review databases for the last case of WPV2.
  If a type 2 poliovirus case is not found in database, declare absence of WPV2 specifying the period reviewed.
    Ex: From February 1985 – April 2015 there has been no detection of WPV 2.
  At the same time, the regional network laboratories for diagnosis will also be consulted (CARPHA)

## Slide 7: Containment of poliovirus
National or Sub-Regional Polio Containment Coordinators need to be assigned.
  Letter went to countries requesting NPCC, but it is up to the Caribbean countries if they prefer 1 sub-regional containment coordinator.
  Inform PAHO by the end of April who the National or Sub-Regional Containment Coordinators are.
Containment Tasks
Inventory, destruction or containment WPV2 + certification- Dec 2015
Inventory, destruction or containment Sabin2 + certification- July 2016
Small working group meeting to define the regional implementation plan- April 2015
Next month will be a virtual meeting where all Containment Coordinators will be invited.

## Slide 8: Poliovirus Containment Next Steps
Countries: Certification GAPIII
RCC: Verification of GAPIII
GCC
Inventory, destruction or Containment
WPV + VDPV + Sabin: beginning with type 2
GCC

## Slide 9: Switch from tOPV to bOPV
tOPV
bOPV

## Slide 10: OPV2 Removal
90% of cVDPV cases are from poliovirus type 2
1/3 of all VAPP cases, globally, are caused by
poliovirus type 2
Type 2 interferes with the immunologic response for types 1 and 3
Notes: Doc. “Preparing for the withdrawal …….”

## Slide 11: Objective 2 of the PEESP has three stages
Introduction
Switch
Remove OPV
tOPV to bOPV
bOPV
Of at least one dose of IPV into routine vaccination program.
By end of 2015
2016
2019-2020

## Slide 12: OPV 2 Removal
The switch is scheduled to be globally synchronized in April 2016 (to reduce risk of re-emergence of type 2 cVDPVs)
145 countries use tOPV: 122 tOPV only and 23 IPV + tOPV
Global absence of persistent circulation of cVDPV2, beginning March 2015
Countries will select one day for the switch within the globally established two week window.

## Slide 13: Switch Protocol
Finalized in mid-April
A draft version could be shared with countries already

## Slide 14: Adequate stocks of tOPV and bOPV
Important to have adequate inventory of tOPV stock at all levels.
Forecasting of tOPV and bOPV demand
Estimate tOPV demand to avoid high wastage of tOPV, yet at the same time avoiding stock-outs before the switch.
Estimate the demand for bOPV and plan to make sure that the vaccine arrives to the country with adequate time and quantities.

## Slide 16: 4 Switch Phases
PLAN
(by end Q2 2015)
PREPARE
IMPLEMENT
VALIDATE

## Slide 17: Phase 1 - Plan
Plan
Q2/15
Establish switch coordination committees
Analysis of current situation
Prepare draft Switch plan
Notes: P9 guidelines

## Slide 18: Situational Analysis
tOPV stock inventory at all levels
Frequency of tOPV distribution to the different levels
Regulatory requirements for use of bOPV in routine program
Use of OPV in private sector
Identify possible barriers to the switch
Laws of country for the safe disposal of tOPV after the switch
Identify professionals that have been involved in the removal of another vaccine
Availability of financial resources
Notes: P9 guidelines

## Slide 19: 2nd Phase - Preparation
Preparation
May 2015 – March 2016
Communication Strategy
tOPV inventory and submission of 2016 demand
Plan for bOPV demand and distribution
Ensure financial resources
Plan for training, supervision and monitoring
Update information systems
Determine final destination for tOPV destruction
Determine Switch Date
Notes: P9 guidelines

## Slide 20: Financial Resources – Switch
Preparation for the switch should include programming funds necessary to finance the following activities:
Stock Monitoring
Improving cold chain for tOPV and bOPV
Training health personnel
Withdrawing tOPV (transportation)
Destruction of residual tOPV stock
Communication
Others: Supervision, Monitoring, etc.

## Slide 21: 3rd Phase - Implementation
Implementation
Train health workers and switch monitors
Deliver bOPV to vaccination sites
Recall and destruct remaining tOPV
Notes: P9 guidelines

## Slide 22: 4th Phase – Validation
Validation
2 weeks after the switch
Selected site visits
Revision and validation of report
Final NCC report
Notes: P9 guidelines

## Slide 23: Switch
After the decision is made by SAGE for the switch date (in October 2015) there will be no turning back, even if a new cVDPV2 is detected.

## Slide 24
http://www.polioeradication.org/Resourcelibrary/Strategyandwork.aspx

## Slide 25: Questions
Would it be useful to receive a draft version (almost final) of the guidelines for preparing the national plan for the switch?
Would it be more convenient to establish a single regional date for the switch or for each country to define the best date within the period of two weeks set by WHO?
Notes: P9 guidelines

## Slide 26: Questions
Would it be useful to receive a draft version (almost final) of the guidelines for preparing the national plan for the switch?
Would it be more convenient establish a single regional date for the switch or for each country to define the best date within the period of two weeks set by WHO?
Regional Polio Meeting: 17 - 21 August
EPI Manager
Professional responsible for acute flaccid paralysis (AFP) surveillance,
Network of laboratories responsible for the diagnosis of polio (CARPHA – Caribbean )
National/ Polio Containment Coordinators
PAHO Immunization Focal Points
Notes: P9 guidelines

## Slide 27
Timeline: Switch and containment activities
Chart: 
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Immediately
Form National Certification Committees (memo 25/2)
Confirm date of last WPV2 (carta Dra. Etienne 2/4)
Assign National Polio Containment Coordinator (carta Dra. Etienne 2/4)
2015
2016
Adjust tOPV and bOPV orders
Switch monitors identified
IMPLEMENT
Train monitors
Train health staff
Distribute bOPV
SWITCH PERIOD
VALIDATE
tOPV disposal
Validation by switch monitors
Validation by NCC
tOPV and bOPV 2016
tOPV inventory
Draft Switch Plan
Inventory of Labs that store WPV, PV Sabin and potentially infectious materials
Destroy all WPV2 or contain in essential facilities
destroy or contain PV Sabin 2 in essential facilities
World Health Assembly
SAGE
Confirmation of switch dates
Prepare
Establish management structure