## PHASE 1
NATIONAL EXPANDED PROGRAM ON IMMUNIZATION PERFORMANCE MONITORING TOOL
ANNEX F. ACTIVITIES SCHEDULE
COUNTRY: ______________ YEAR:_____________
Category | Sub-category | Activity description | Responsible person/team | Associated Annex | Estimated timeframe | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month
[6 empty] | Weeks |  |  |  | Weeks |  |  |  | Weeks |  |  |  | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 1: Preparation | [21 empty] | Activity status
Installation phase | Country acceptance and agreement | Share and present the monitoring tool to the Member State. | PAHO Regional Office | Annex C | [18 empty] | No progress | bar: Weeks 1
|  | Secure consultant contract that will support all self-assessment activities | PAHO Regional and Country offices | Annex D | [18 empty] | Ongoing | bar: Weeks 1 to Weeks 4
|  | Provide the consultant with the necessary training on all procedures and documents involved in the self-assessment process. | PAHO Regional Office | Annex E | [18 empty] | Completed | bar: Weeks 4
Annex 2 | bar: Weeks 4
|  | Formalize the inclusion of National Coordination Committee (NCC) members. PAHO/CIM focal point is expected to carry out secretariat duties. | MoH EPI | bar: Weeks 1 to Weeks 2
|  | Prepare a draft budget estimate for the EPI self-assessment (consultant contract, travel, self-assessment sessions, etc.). | PAHO Regional and Country office | bar: Weeks 2
|  | Train the NCC on the purpose of the tool, the role of the NCC in the EPI self-assessment and expected results. | PAHO country office and Consultants | Annex1 | bar: Weeks 4
Annex 2 | bar: Weeks 4
|  | Define a tentative date for the implementation of the national EPI self-assessment. | NCC | Annex F | bar: Weeks 1
Situation analysis | Collect and link documents | Identify the stakeholders responsible for each EPI component. | NCC and Consultant | bar: Weeks 2 to Weeks 1
|  | Manage access to and collection of EPI information for the last 5 years. | NCC and Consultant | Annex 3 | bar: Weeks 1 to Weeks 3
|  | Review and discuss with stakeholders the EPI data documents/reports for the last 5 years. | NCC and Consultant | Annex 3 | bar: Weeks 1 to Weeks 3
|  | Review the documents received for each component and link them to the questions in the tool. | NCC and Consultant | bar: Weeks 1 to Weeks 3
|  | Identify questions that cannot be linked to the documents or data reports received | NCC and Consultant | bar: Weeks 3
|  | Contact the responsible persons once again to locate the remaining documents. | NCC and Consultant | bar: Weeks 3
|  | Link the documents/data received to the remaining questions in the adapted Excel version of the tool. | NCC and Consultant | bar: Weeks 3
|  | Set up a folder or drive with all documents organized by component, which is permanently available to national EPI staff. | NCC and Consultant | bar: Weeks 3
| Completion of situation analysis report | Finalize the situation analysis report. | Consultant | Annex 4A | bar: Weeks 4
|  | Finalize the presentation of the situation analysis. | Consultant | Annex 4B | bar: Weeks 4
|  | Validate the situation analysis report, paying special attention to: - The linkage of the documents/data received to the remaining questions in the adapted Excel version of the tool, - Completeness, synthesis, documentary support, - Strengths and challenges of EPI, routine vaccination and COVID-19 vaccination, - The components of routine vaccination and COVID-19 vaccination that present the greatest challenges. | NCC | bar: Weeks 4
|  | Share the situation analysis report and the folder with the documents of the last 5 years of the EPI with the PAHO Regional Office. | NCC | bar: Weeks 4
|  | Provide feedback to the situation analysis report. | PAHO Regional Office | bar: Weeks 4
|  | Distribute the documents/data received to the remaining questions in the adapted version of the tool in Excel.Share the situation analysis report with the national authorities. | NCC | bar: Weeks 4
Tool adjustment | Tool adjustment | Adjust the tool to the country context (e.g., N/A questions, terminology for administrative levels, non-applicable questions, vocabulary terms, names of official institutions, etc.). - Identify the need for adaptation of specific aspects of the tool (PDF document) to the country context. | NCC, Consultant - PAHO Regional Office | Annex 5 | bar: Weeks 4
|  | Link the documents/data received to the remaining questions in the adapted Excel version of the tool. | NCC and Consultant | bar: Weeks 4
|  | Review the application of adjustment guidelines to the tool. - Verify linkage of documents/data received to the remaining questions in the adapted Excel version of the tool. - Submit adjustments to RCT for incorporation. | Consultant and PAHO Regional Office | Annex 5 | bar: Weeks 4
|  | Complete the linking of the received documents/data to the remaining questions in the customized version of the tool in Excel.Receive the customized version of the tool for application. | NCC and Consultant | bar: Weeks 4
Note: symbolizes the period of time in which it is suggested to complete the activity ideally.

## PHASE 2
NATIONAL EXPANDED PROGRAM ON IMMUNIZATION PERFORMANCE MONITORING TOOL
ANNEX F. ACTIVITIES SCHEDULE
COUNTRY: ______________ YEAR:_____________
Category | Sub-category | Activity description | Responsible person/team | Associated Annex | Estimated timeframe | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month
[6 empty] | Weeks |  |  |  | Weeks |  |  |  | Weeks |  |  |  | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 2: Implementation | [21 empty] | Activity status
Budget | Costing | Complete and manage the budget to implement the field visits and self-assessment workshops at the national level. | NCC and consultant | Annex 6 | [18 empty] | No progress | bar: Weeks 1
Preparation: sub-national and local levels | Plan and implement self-assessment at subnational and local levels. | Select the subnational (province/state/department) and local (health facility) areas where the self-assessment questionnaires will be administered. | NCC and consultant | Annex 7 | [18 empty] | Ongoing | bar: Weeks 2
|  | Coordinate with the EPI officers of the subnational and local areas to assess the readiness and logistics for receiving the field visits. | NCC and consultant | Annex 2 | [18 empty] | Completed | bar: Weeks 2
|  | Finalize dates for field visits. | NCC and consultant | bar: Weeks 3
|  | Identify and train 5-6 people from the national level who will travel to the subnational level to administer the self-assessment tool. | NCC and consultant | bar: Weeks 3
|  | Organize and share all logistical details with the persons who will travel to the sub-national level to support the implementation of the self-assessment. | NCC and consultant | Annex 8A. Guidelines for the implementation of self-assessment at the subnational level | bar: Weeks 3 to Weeks 4
|  | Verify the list of logistical tasks in preparation for implementing the sub-national and local self-assessment. | NCC and consultant | bar: Weeks 3 to Weeks 4
|  | Travel to the sub-national level to facilitate the self-assessment. | Designated person/s | bar: Weeks 3 to Weeks 4
Implementation: sub-national and local levels | Sub-national level | Administer questionnaire (components #2- #13) to subnational level officials in each selected province/state/department. | Designated persons from the national level | Annex 8B. Presentation for the sub-national level | bar: Weeks 1
| Local Level | Administer the questionnaire (component #14) to local level officials in each selected health facility. | Designated persons from the national level | Annex 14 | bar: Weeks 1
| Score compilation | Compile the scores and grades for each question into a single Excel version of the tool. | Consultant | bar: Weeks 1
Preparation: self-assessment at the national level | Define workshop agenda | Develop the agenda for the national level self-evaluation workshops. One component will be reviewed in each session with two simultaneous sessions per day, for a period of 5 days. | Consultant | Annex 10 | bar: Weeks 2
Annex 12 | bar: Weeks 2
Annex 13 | bar: Weeks 2
|  | Validate the agenda for the self-assessment workshops. | NCC | bar: Weeks 3
| Call for participants | Identify participants for each EPI component. | NCC and consultant | Annex 9A | bar: Weeks 3
Annex 9B | bar: Weeks 3
|  | Send official invitations to participants along with the agenda and a summary of the methodology and tool. | NCC and consultant | bar: Weeks 3
| Event preparation | Select work areas (rooms) and manage logistics for the development of the workshops. - Face-to-face sessions: management of spaces, furniture, screens, sound, computer, printed materials, etc. - Coordination of online sessions with Zoom / Teams administrators, advance dissemination of schedules, session links, confirmation of virtual participants (i.e. advisors from the PAHO Regional Office), sound check, etc. | Consultant | Annex 2 | bar: Weeks 3
| Preparing the sessions | Lead a simulation exercise to ensure that all secretariat members are trained to execute their roles during the national level discussion sessions. The stages are: a. Introduction of the IAP component and related items. b. Conducting the discussion sessions on the self-evaluation of each component. c. Consensus on the level of maturity to choose to represent the current status of each item within each component. d. Wrap-up discussion at the end of the workshop with participants. e. Debriefing session at the end of the day with secretariat members. | Consultant | Annex 11 | bar: Weeks 3
|  | Create a PowerPoint presentation (PPT) that includes each of the items in each component of the monitoring tool (one item/question + its maturity scale per slide). | Consultant | Annex 14 | bar: Weeks 3
Implementation: self-assessment at the national level | Discussion sessions | Opening ceremony and agenda development. Presentation of session structure and self-assessment methodology. | NCC | Annex 10 | bar: Weeks 4
|  | Application of self-assessment by component according to agenda: 1. Political priority 2. Planning and programming 3. Organization and coordination 4. Epidemiological surveillance 5. Human resources and financial planning 6. Training and supervision 7. Information system 8. Cold chain 9. Supply of vaccines 10. Evaluation and research 11. Social communication 12. Safe vaccination 13. Execution 14. Vaccination against COVID-19 | Participants, NCC, PAHO Regional Advisors | Annex 11 | bar: Weeks 4
Annex 13 | bar: Weeks 4
Annex 14 | bar: Weeks 4
Annex 15 | bar: Weeks 4
| Wrap-up | Lead a debriefing session at the end of each day with all secretariat members. | Consultant | bar: Weeks 4
|  | Consolidate notes from each workshop into an online unit, summary of main challenges and actions required, established scores. | Consultant | bar: Weeks 4
|  | Consolidate action item notes for the closing ceremony. | Consultant | bar: Weeks 4
| Closing of the discussions | Implement a self-assessment closing ceremony, with review of results and main recommendations. | NCC and consultant | bar: Weeks 4
Note: symbolizes the period of time in which it is suggested to complete the activity ideally.

## PHASE 3
NATIONAL EXPANDED PROGRAM ON IMMUNIZATION PERFORMANCE MONITORING TOOL
ANNEX F. ACTIVITIES SCHEDULE
COUNTRY: ______________ YEAR:_____________
Category | Sub-category | Activity description | Responsible person/team | Associated Annex | Estimated timeframe | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month
[6 empty] | Weeks |  |  |  | Weeks |  |  |  | Weeks |  |  |  | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 3: Follow-up | [21 empty] | Activity status
Scoring | Final scoring | Compile the scores for each component using only the scores selected at the national level. | Consultant | [19 empty] | No progress | bar: Weeks 1
| Data visualization | Review and validate the final score for each component. | NCC | [19 empty] | Ongoing | bar: Weeks 1
Reports | Final report | Identify priority areas of the different components for the country. | NCC | [19 empty] | Completed | bar: Weeks 1
|  | Prepare a final report and PPT based on the situation analysis, the sub-national and local level visits, and the national level discussions. | Consultant | Annex 16 | bar: Weeks 2
|  | Validate the final report and PPT. | NCC and PAHO Regional Office | bar: Weeks 2
|  | Present the results of the self-assessment to the national authorities. | NCC | bar: Weeks 2
| Action Plan | Recompile the recommendations and proposals for action discussed during the national level sessions. | Consultant | bar: Weeks 2
|  | Develop a draft action plan. | Consultant | Annex 17 | bar: Weeks 3
|  | Finalize and validate the action plan. | NCC and PAHO Regional Office | bar: Weeks 4
|  | Submit action plan to national authorities. | NCC | bar: Weeks 4
Note: symbolizes the period of time in which it is suggested to complete the activity ideally.
PAHO-CIM